## AFNT Sprints
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS
Alistana Fitness and Nutrition Tracker (AFNT) |  |  | Ali Suhail |  | 2024-10-01 | 2024-05-13 | 58%
At Risk? | TASK NAME | PHASE TYPE | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 – PLANNING & DESIGN |  | 2023-10-05 | 2023-12-31 | 88
Yes | Write down requirements | Planning | 2023-10-05 | 2023-10-16 | 12 | Complete | High
Yes | Project Proposal | Planning | 2023-10-20 | 2023-10-25 | 6 | Complete | High
Yes | Decide Arduino Watch Component | Planning | 2023-10-21 | 2023-10-26 | 6 | Complete | High
Yes | Pre-Ethical Checklist | Planning | 2023-11-06 | 2023-11-06 | 1 | Complete | High | Received First Arduino Watch Parts on 04/11/2024
Yes | Ethical Checklist | Planning | 2023-11-06 | 2023-11-06 | 1 | Complete | High
Yes | Research Kivy GUI | Planning | 2023-11-05 | 2023-12-02 | 28 | Complete | High
No | Design AFNT Logo | Planning | 2023-12-14 | 2023-12-14 | 1 | Complete | Medium
No | Create Usecase diagrams for Admin Management Website | Design | 2023-12-07 | 2023-12-15 | 9 | Complete | High
No | Create Usecase diagrams for AFNT App | Design | 2023-12-07 | 2023-12-15 | 9 | Complete | High
No | Create Usecase diagrams for Arduino Watch | Design | 2023-12-07 | 2023-12-15 | 9 | Complete | High
Yes | Create LocalDB Schema | Design | 2023-12-16 | 2023-12-20 | 5 | Complete | High
Yes | Create CentralDB Schema | Design | 2023-12-16 | 2023-12-20 | 5 | Complete | High
No | Create AFNT Architecture Diagram | Design | 2023-12-21 | 2023-12-21 | 1 | Complete | High
Yes | Setup Login Server | Server | 2023-12-21 | 2023-12-25 | 5 | Complete | High
Yes | Setup Admin Login Server | Server | 2023-12-21 | 2023-12-25 | 5 | Complete | High
Yes | Setup Account Server | Server | 2023-12-21 | 2023-12-25 |  | Complete | High
Yes | Create Class diagram for AFNT App | Design | 2023-12-22 | 2023-12-26 | 5 | Complete | High
Yes | Create Class diagram for Central and Local DB | Design | 2023-12-22 | 2023-12-26 | 5 | Complete | High
No | Create AFNT UI Sketches | Design | 2023-12-27 | 2023-12-29 | 3 | Complete | High | Delayed to 16/01/2024
No | Create AM Website UI Sketches | Design | 2023-12-29 | 2023-12-30 | 2 | Complete | High | Delayed to 16/01/2024
No | Add Usecase descriptions | Design | 2023-12-30 | 2023-12-31 | 2 | Complete | High | Delayed to 16/01/2024
| SPRINT 2 – PHASE 1 IMPLEMENTATION & PIP |  | 2024-01-01 | 2024-01-31 | 31
Yes | [#1] AMW Login Screen | Website | 2024-01-01 | 2024-01-03 | 3 | Complete | High
Yes | Implement Central DB | Database | 2024-01-04 | 2024-01-10 | 7 | Complete | High
Yes | Implement LocalDB | Database | 2024-01-04 | 2024-01-10 | 7 | Complete | High | Implemented Phase 1 and 1,5
Yes | [#1] AFNT Login Screen | Application | 2024-01-11 | 2024-01-16 | 6 | Complete | High
Yes | [#1] AFNT Registration Screen | Application | 2024-01-16 | 2024-01-18 | 3 | Complete | High
Yes | Create Poster | PIP | 2024-01-15 | 2024-01-21 | 7 | Complete | High
Yes | Complete Video Demo | PIP | 2024-01-16 | 2024-01-22 | 7 | Complete | High
Yes | Assemble Arduino Watch | Phase 4 | 2024-01-23 | 2024-01-23 | 1 | Complete | High | Final Arduino Watch parts arrived on 23/01/2024
Yes | Test second batch of Arduino Watch | Phase 4 | 2024-01-23 | 2024-01-23 | 1 | Complete | High
Yes | Finish Literature Review | Report | 2024-01-15 | 2024-01-24 | 10 | Complete | High
Yes | PIP Demo | PIP | 2024-01-24 | 2024-01-24 | 1 | Complete | High
| SPRINT 3 – PHASE 3 IMPLEMENTATION |  | 2024-02-01 | 2024-03-23 | 52
Yes | [#2] AFNT Dashboard | Application | 2024-02-01 | 2024-02-02 | 2 | Complete | High
Yes | [#23] Water Intake Screen | Application | 2024-02-01 | 2024-02-02 | 2 | Complete | High
Yes | [#26] Water Intake Plots Screen | Application | 2024-02-01 | 2024-02-02 | 2 | Complete | High
Yes | [#24] Body Statistics Screen | Application | 2024-02-03 | 2024-02-06 | 4 | Complete | High
Yes | [#25] Body Statistics Plots Screen | Application | 2024-02-03 | 2024-02-06 | 4 | Complete | High
Yes | [#4, #8, #12, #13] Workout History Screen | Application | 2024-02-07 | 2024-02-20 | 14 | Complete | High
Yes | Fix Github problem | Github | 2024-02-21 | 2024-02-21 | 1 | Complete | High
Yes | [#5, #11, #16] Exercise Log Screen | Application | 2024-02-21 | 2024-02-22 | 2 | Complete | High
Yes | [#8, #10, #11, #12] Workout Allocate Screen | Application | 2024-02-26 | 2024-03-01 | 5 | Complete | High
Yes | [#10] Workout Create Screen | Application | 2024-03-02 | 2024-03-03 | 2 | Complete | High
Yes | [#14] Exercise Create Screen | Application | 2024-03-03 | 2024-03-03 | 1 | Complete | High
Yes | [#11, #16] Exercise Allocate Screen | Application | 2024-03-04 | 2024-03-08 | 5 | Complete | High
Yes | [#11] Exercise Log Allocate Screen | Application | 2024-03-09 | 2024-03-09 | 1 | Complete | High
No | Gym Finder Screen | Application | 2024-03-08 | 2024-03-10 | 3 | Needs Review | Low
Yes | Update Usecase Diagrams | Design | 2024-03-15 | 2024-03-20 | 6 | Complete | Medium | Travelled to Kuwait on 16/03/2024, due to urgent personal matter
Yes | Update Class Diagrams | Design | 2024-03-21 | 2024-03-22 | 2 | Complete | Medium
Yes | Report Draft Submission to Supervisor | Report | 2024-03-20 | 2024-03-23 | 4 | Complete | High
| SPRINT 4 – PHASE 4 IMPLEMENTATION |  | 2024-03-24 | 2024-05-13 | 51
Yes | Implement Step Count Functionality | Phase 4 | 2024-03-24 | 2024-03-25 | 2 | Complete | High
Yes | Implement Blood Oxygen Functionality | Phase 4 | 2024-03-24 | 2024-03-25 | 2 | Complete | High
Yes | Implement Heart Rate Functionality | Phase 4 | 2024-03-25 | 2024-03-25 | 1 | Complete | High
Yes | Implement Date and Time Functionality | Phase 4 | 2024-03-25 | 2024-03-25 | 1 | Complete | High
Yes | Arduino Bluetooth Data Transfer | Phase 4 | 2024-03-31 | 2024-04-03 | 4 | In Progress | High
Yes | Arduino Screen | Phase 3 | 2024-04-04 | 2024-04-13 | 10 | Needs Review | High | Return flight to UK on 13/04/2024
Yes | Meal History | Phase 3 | 2024-04-15 | 2024-04-15 | 1 | Needs Review | Medium
Yes | Food Item Log | Phase 3 | 2024-04-16 | 2024-04-17 | 2 | Not Started | Medium
Yes | Meal Allocate Screen | Phase 3 | 2024-04-17 | 2024-04-18 | 2 | Not Started | Medium
Yes | Meal Create Screen | Phase 3 | 2024-04-19 | 2024-04-20 | 2 | Not Started | Medium
Yes | Final Report | Report | 2024-04-20 | 2024-04-24 | 5 | Complete | High

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold