## 4r2w1F7l - afnt-project
Card | Card Name | Due Date | Due Complete
TO-DO | Food Item Log | 2024-04-21 | FALSE
| Meal Create Screen | 2024-04-21 | FALSE
| Food Item Create Screen | 2024-04-21 | FALSE
| Food Item Allocate Screen | 2024-04-21 | FALSE
IN-PROGRESS | [#2] AMW Main Page | 2024-03-01 | FALSE
| Gym Finder Screen | 2024-03-15 | FALSE
| Arduino Bluetooth Data Transfer | 2024-04-20 | FALSE
| Meal Allocate Screen | 2024-04-21 | FALSE
SPRINT 4 PHASE 4 IMPLEMENTATION | Final Report | 2024-04-24 | TRUE
| Arduino Watch | 2024-04-12 | TRUE
| Meal History Screen | 2024-04-13 | TRUE
| Arduino Screen | 2024-04-20 | TRUE
SPRINT 3 PHASE 3 IMPLEMENTATION | [#2] AFNT Dashboard | 2024-02-01 | TRUE
| [#23] Water Intake Screen | 2024-02-01 | TRUE
| [#26] Water Intake Plots Screen | 2024-02-01 | TRUE
| [#24] Body Statistics Screen | 2024-02-05 | TRUE
| [#25] Body Statistics Plots Screen | 2024-02-05 | TRUE
| [#4, #8, #12, #13] Workout History Screen | 2024-02-19 | TRUE
| Fix Github problem | 2024-02-20 | TRUE
| [#5, #11, #16] Exercise Log Screen | 2024-02-21 | TRUE
| [#8, #10, #11, #12] Workout Allocate Screen | 2024-02-29 | TRUE
| [#10] Workout Create Screen | 2024-03-02 | TRUE
| [#14] Exercise Create Screen | 2024-03-02 | TRUE
| [#11, #16] Exercise Allocate Screen | 2024-03-07 | TRUE
| [#11] Exercise Log Allocate Screen | 2024-03-08 | TRUE
| Report Draft Submission to Supervisor | 2024-03-22 | TRUE
SPRINT 2 PHASE 1 IMPLEMENTATION & PIP | [#1] AMW Login Screen | 2024-01-03 | TRUE
| Implement Central DB | 2024-01-10 | TRUE
| Implement LocalDB | 2024-01-10 | TRUE
| [#1] AFNT Login Screen | 2024-01-16 | TRUE
| [#1] AFNT Registration Screen | 2024-01-18 | TRUE
| Create Poster | 2024-01-21 | TRUE
| Complete Video Demo | 2024-01-21 | TRUE
| Assemble Arduino Watch Parts | 2024-01-22 | TRUE
| Test second batch of Arduino Watch | 2024-01-22 | TRUE
| Finish Literature Review | 2024-01-24 | TRUE
| PIP DEMO | 2024-01-24 | TRUE
SPRINT 1 PLANNING & DESIGN | Write down Requirements | 2023-10-09 | TRUE
| Complete Project Proposal | 2023-10-25 | TRUE
| Test First Batch of Arduino Watch Components | 2023-11-04 | TRUE
| Pre-Ethical Checklist | 2023-11-06 | TRUE
| Ethical Checklist | 2023-11-06 | TRUE
| Research Kivy GUI | 2023-12-02 | TRUE
| Design AFNT Logo | 2023-12-14 | TRUE
| Create Usecase diagrams for Admin Management Website | 2023-12-15 | TRUE
| Create Usecase diagrams for AFNT App | 2023-12-15 | TRUE
| Create Usecase diagrams for Arduino Watch | 2023-12-15 | TRUE
| Create LocalDB Schema | 2023-12-20 | TRUE
| Create CentralDB Schema | 2023-12-20 | TRUE
| Create AFNT Architecture Diagram | 2023-12-21 | TRUE
| Setup Login Server | 2023-12-25 | TRUE
| Setup Admin Login Server | 2023-12-25 | TRUE
| Setup Account Server | 2023-12-25 | TRUE
| Create Class diagram for AFNT App | 2023-12-26 | TRUE
| Create Class diagram for Central and Local DB | 2023-12-26 | TRUE
| Create AFNT UI Sketches | 2024-01-16 | TRUE
| Create AM Website UI Sketches | 2024-01-16 | TRUE
| Add Usecase descriptions | 2024-01-15 | TRUE
SUPERVISOR-MEETINGS | 09/10/2023 - Martin Serpell | 2023-10-09 | TRUE
| 16/10/2023 - Eman Qaddoumi | 2023-10-16 | TRUE
| 16/10/2023 - Martin Serpell | 2023-10-16 | TRUE
| 19/10/2023 - Eman Qaddoumi | 2023-10-19 | TRUE
| 23/10/2023 - Martin Serpell | 2023-10-23 | TRUE
| 30/10/2023 - Martin Serpell | 2023-10-30 | TRUE
| 06/11/2023 - Eman Qaddoumi | 2023-11-06 | TRUE
| 21/12/2023 - Martin Serpell | 2023-12-21 | TRUE
| 12/01/2023 - Eman Qaddoumi | 2023-01-12 | TRUE
| 25/01/2024 - Eman Qaddoumi | 2024-01-25 | TRUE
| 09/02/2024 - Eman Qaddoumi | 2024-02-09 | TRUE
| 23/02/2024 - Eman Qaddoumi | 2024-02-23 | TRUE
| 27/03/2024 - Eman Qaddoumi | 2024-03-27 | TRUE
| 19/04/2024 - Eman Qaddoumi | 2024-04-19 | TRUE
| 23/04/2024 - Eman Qaddoumi | 2024-04-23 | TRUE