## Sheet1
Date | Time | Location | Type | Attendies | Agenda | Status | Updates
2023-10-09 | 15:05-16:00 | X Block | Supervisor Meeting | Ali Suhail Martin Serpell | Project Idea Discussion. | Complete | Decided to proceed with a workout tracker application called Alistana Fitness and Nutrition Application (AFNA) which is Phase 3.
2023-10-09 | 19:00-23:00 | Home | Project Work | Ali Suhail | Write down Objectives and Requirements. Create a Database Schema (DBv1 & DBv2). | Complete | Completed Intial Objectives and Requirements. Created the first 2 versions of that DBMS (DBv1 & DBv2) which is Phase 1.
2023-10-11 | 19:00-22:00 | Home | Project Work | Ali Suhail | Complete Phase 1 (Database) of the Project. | Complete | Made good progress. Completed around 50% of the database design schema. Completed AFNA DBv3 using Microsoft Access.
2023-10-16 | 12:45-13:05 | E Block | Supervisor Meeting | Ali Suhail Eman Qaddoumi | Project Report Advice & Project Discussion. | Complete
2023-10-16 | 15:05-17:00 | X Block | Supervisor Meeting | Ali Suhail Martin Serpell Yie Nian Chu | Project Report Advice & Project Discussion. | Complete | Expanded the scope of the project by adding an Arduino watch (Phase 4) that will be used to collect heart rate and blood oxygen levels using an oximeter. Changed the name of the application to Alistana Fitness & Nutritional Tracker (AFNT).
2023-10-19 | 15:13-15:47 | Online | Supervisor Meeting | Ali Suhail Eman Qaddoumi | Final Year Project Decision. | Complete
2023-10-23 | 15:05-16:05 | X Block | Supervisor Meeting | Ali Suhail Martin Serpell Yie Nian Chu | Advice on Database servers and Arduino Watch. | Complete | Changed the design to use MySQL lite instead of MySQL servers due to cost.
2023-10-24 | 18:00-01:00 | Home | Project Work | Ali Suhail | Complete and Finalize Objectives and Requirements. Complete Project Proposal. Research on SQLite and Servers. Complete DBv4 Schema using Microsoft Access. Order hardware for Arduino watch (Phase 4). | Complete | Partially complete Objectives and Requirements (50%). Partially complete Project Proposal (60%). Decided to proceed with SQLite for Local DB, Still need to do research on servers. Partially complete DBv4 Schema (70%). Ordered Arduino Watch hardware parts (incl. spare) at a cost of £93.45.
2023-10-25 | 14:00-18:00 | Home | Project Work | Ali Suhail | Complete and Finalize Objectives and Requirements Complete Project Proposal Complete DBv4 Schema using Microsoft Access | Complete | Partially complete Objectives and Requirements (90%). Completed and Submitted Project Proposal at 19:33. Completed DBv4 Schema.
2023-10-25 | 14:00-18:00 | Home | Project Work | Ali Suhail | Complete and Submit the Project Proposal | Complete | Completed and Submitted Project Proposal at 19:33.
2023-10-26 | 18:20:00-21:00 | Home | Project Work | Ali Suhail | Complete and Finialize Objectives and Requirements | Complete | Completed Objectives and Requirements.
2023-10-30 | 15:05-15:20 | X Block | Supervisor Meeting | Ali Suhail Martin Serpell Yie Nian Chu | Project Progress and Server related Questions | Complete
2023-11-04 | 19:00:20:50 | Home | Arduino Watch | Ali Suhail | Test First Batch of Arduino Watch Components | Complete | Recieved First Batch of Arduino Watch Parts
2023-11-06 | 15:35-16:10 | E Block | Supervisor Meeting | Ali Suhail Eman Qaddoumi | Pre-Ethical Checklist Ethical Checklist | Complete | Completed both Pre-Ethical and Ethical Checklist with Supervisor.
2023-12-14 | 19:00-02:00 | Home | Webpage | Ali Suhail | Design AFNT Logo Create Login UI Webpage Research on Python GUI Frameworks Arduino Research | Complete | Completed AFNT Logo Design, Login UI.
2023-12-14 | 19:00-02:00 | Home | UML Diagram | Ali Suhail | Complete UseCase Diagram | Complete | 90% Complete UseCase.
2023-12-15 | 21:00-02:00 | Home | Server | Ali Suhail | Establish Local Host Server Implement Database Complete UseCase Diagram Decide which Python GUI Framework to use | Complete | Completed Establishing the LocalHost Server. Completed UseCase Diagram. Decided to use Pyhon Kivy for GUI Design.
2023-12-17 | 21:40-22:30 | Home | UML Diagram | Ali Suhail | Started working on UML Class Diagram Research SQLite | Complete | Class Diagram around 10% complete Did some research and practice with SQLite.
2023-12-18 | 03:00-04:10 | Home | UML Diagram | Ali Suhail | Worked on Class Diagram Research SQLite | Complete | Class Diagram around 50% complete.
2023-12-19 | 22:00-01:10 | Home | Webpage | Ali Suhail | Implement Login System Implement SQLite Database (Phase 1.5) | Complete | Completed and Implemented the Login System. Completed Class Diagram. Database Implementation 5% complete
2023-12-20 | 20:00-23:00 | Home | Database | Ali Suhail | Implement the Local Database Implement Main Page for Website | Complete | LocalDB 15% complete. Main Page 5% complete. microSD card for Arduino Watch Arrived
2023-12-21 | 10:00-11:15 | X Block | Supervisor Meeting | Ali Suhail Martin Serpell | Discuss Project Progress Questions Related to UML Diagrams and Project's Architecture Design Questions about Report Writing | Complete
2023-12-21 | 22:00-02:05 | Home | UML Diagram | Ali Suhail | Create AFNT Architecture Diagram Improve UseCase and Class Diagram | Complete | Improved AFNT's Project Design. Created AFNT Architecture Diagram. Improved UseCase Diagram.
2023-12-22 | 21:30-22:20 | Work | UML Diagram | Ali Suhail | Improve UseCase and Class Diagrams Create Sequence Diagram Implement Phase 1.5 (Local DB) | Complete | Usecase improvement 10% done. Did research on Sequence Diagram. Didn't have time for Phase 1.5 because of work.
2023-12-23 | 02:00-05:00 | Home | UML Diagram | Ali Suhail | Improve Class and UseCase Diagram | Complete | Completed Improving UseClase Diagram. Completed 60% Class Diagram.
2023-12-24 | 01:00-05:00 | Home | UML Diagram | Ali Suhail | Complete Class Diagram Improvement Complete UI Sketches for Admin Management Website | Complete | Completed Class Diagram Improvments. Finished 60% UI Sketches for AM Website.
2023-12-25 | 12:00-05:00 | Home | UI Sketches | Ali Suhail | Implement Phase 1.5 Complete AM Website UI Sketches | Complete | Completed AM Website UI Sketches
2023-12-26 | 00:00-03:30 | Home | Database | Ali Suhail | Implement Phase 1.5 | Complete | Implemented 50% of Phase 1.5
2023-12-26 | 19:00-00:00 | Home | Database | Ali Suhail | Implement Phase 1 Implement Phase 1.5 | Complete | Implemented Phase 1. Implemented 90% of Phase 1.5.
2023-12-27 | 19:10-20:00 | Home | Database | Ali Suhail | Implement Phase 1.5 | Complete | Implemented Phase 1.5.
2023-12-02 | 19:00-22:00 | Home | Application | Ali Suhail | Research on Kivy GUI | Complete
2024-01-12 | 12:40-13:45 | Online | Supervisor Meeting | Ali Suhail Eman Qaddoumi | Project Progress UML Design Questions | Complete
2024-01-13 | 07:00-12:00 | Home | UI Sketches | Ali Suhail | Start AFNT App UI Sketches Research on Kivy GUI | Complete | Completed around 10% UI Sketches
2024-01-14 | 07:00-12:00 | Home | UI Sketches | Ali Suhail | Finish AFNT App UI Sketches Research on Kivy GUI | Complete | Completed around 20% UI Sketches
2024-01-15 | 20:00-01:30 | Home | Application | Ali Suhail | Finish AFNT App UI Sketches Research on Kivy GUI Create 1_afnt_login screen | Complete | Completed around 50% UI Sketches Completed around 5% of 1_afnt_login screen
2024-01-16 | 20:00-01:30 | Home | Application | Ali Suhail | Finish UI Sketches Research Kivy GUI Create User Class Complete 1_afnt_login screen | Complete | Completed around 80% of UI Sketches Completed around 90% of 1_afnt_login screen Created User Class
2024-01-17 | 20:00-01:30 | Home | Application | Ali Suhail | Finish UI Sketches Complete registration_screen | Complete | Completed 10% of registration screen
2024-01-18 | 21:00-02:00 | Home | Application | Ali Suhail | Finish UI Sketches Complete registration_screen | Complete | Completed registration screen Partially Completed UI Sketches
2024-01-19 | 21:00-02:01 | Home | Application | Ali Suhail | Finish UI Sketches Start work on Literature Review | Complete | Finished UI Sketches Started work on Literature Review
2024-01-20 | 21:00-02:02 | Home | Report | Ali Suhail | Complete Poster Complete Literature Review Research for Literature Review | Complete | Partial Progress in Poster and Literature Review Partially Completed UI Sketches
2024-01-21 | 20:00-04:00 | Home | Report | Ali Suhail | Complete Poster Complete Introduction Section Complete Literature Review Research for Literature Review | Complete | Completed Introduction Section Completed Poster Completed around 20% of Literature Review
2024-01-22 | 21:00-02:04 | Home | Video Demo | Ali Suhail | Complete Video Demo Complete Literature Review Complete 2_afnt_main screen Complete afnt UI: 3, 4, 5, 6, and 7 | Complete | Completed Video Demo Partially Completed 2_afnt_screen Partially completed afnt UI, 3, 4, 5, 6 Completed around 30% of Literature Review
2024-01-23 | 20:00-02:00 | Home | Report | Ali Suhail | Complete Literacture Review Test Final Batch of Arduino Watch Components Assemble Arduino Watch Prepare for PIP | Complete | Completed around 45% of the Literature Review Received Final Batch of Arduino Watch Parts Tested Arduino Watch Parts Assembled Arduino Watch
2024-01-24 | 13:00-14:30 | 4E13 | PIP | Ali Suhail Mohammad Hosseinabady | Print Poster PIP Presentation and Demo | Complete | Printed Poster Finished PIP Presentation and Demo Eman Qaddoumi could not attend as she was busy
2024-01-24 | 17:00-01:30 | Home | Report Arduino Watch | Ali Suhail | Finish Literature Review Start Programming Arduino Watch | Complete | Finished around 80% of Literature View Implemented Accelerometer Functionality
2024-01-25 | 15:40-16:10 | Online | Supervisor Meeting | Ali Suhail Eman Qaddoumi | PIP Discussion Next Steps with the project | Complete
2024-01-25 | 19:30-03:00 | Home | Report | Ali Suhail | Finish Literature Review | Complete | Finished Literature Review Submited Literature Review
2024-01-26 | 05:00-05:34 | Home | Report Application | Ali Suhail | Submit Literature Review | Complete | Submited Literature Review
2024-01-29 | 20:00-03:00 | Home | Report Application | Ali Suhail | Review Literature Review | Complete | Resubmitted Literature Review Finished 80% dashboard and water intake screen
2024-01-30 | 20:00-02:00 | Home | Application | Ali Suhail | Finish dashboard screen Finish water intake screen | Complete | Finished 70% Dashboard Screen Finished 10% of Water Intake Screen
2024-01-31 | 20:00-02:00 | Home | Application | Ali Suhail | Finish dashboard screen Finish water intake screen | Complete | Finished 70% Dashboard Screen Finished 70% of Water Intake Screen
2024-02-01 | 20:00-02:00 | Home | Application | Ali Suhail | Finish dashboard screen Finish water intake screen Finish body stats screen | Complete | Dashboard screen 90% complete Water intake screen 90% finished Started work on body screen
2024-02-02 | 20:00-02:00 | Home | Application | Ali Suhail | Finish dashboard screen Finish water intake screen Finish body stats screen | Complete | Finished Dashboard Screen Finished Water Intake Screen Body Stats 10% complete
2024-02-04 | 20:00-03:00 | Home | Application | Ali Suhail | Finish body stats screen | Complete | Finished 50% Body Stats Screen
2024-02-05 | 20:30-02:00 | Home | Application | Ali Suhail | Finish body stats screen | Complete | Finished 90% Body Stats Screen
2024-02-06 | 20:30-02:00 | Home | Application | Ali Suhail | Finish body stats screen Start workout screen Start exercise screen | Complete | Finished Body Stats Screen Finished 5% Workout and Exercise Screen
2024-02-07 | 23:45-01:00 | Home | Application | Ali Suhail | Finish workout screen Finish exercise screen | Complete | Finished 5% Workout and Exercise Screen
2024-02-08 | 23:45-03:00 | Home | Application | Ali Suhail | Finish workout screen Finish exercise screen Improve UI Design | Complete | Improved UI Design
2024-02-09 | 13:00-13:30 | Online | Supervisor Meeting | Ali Suhail Eman Qaddoumi | Discuss Project Progress | Complete
2024-02-10 | 12:00-02:00 | Home | Application | Ali Suhail | Add Step Count Graphs in Body Stats Complete Workout History Screen Research Datatables in KivyMD | Complete | Completed and Implemented Step Count Graph Completed 20% Workout History Screen
2024-02-11 | 22:30-02:00 | Home | Application | Ali Suhail | Complete Workout History Screen | Complete | Completed 40% Workout History Screen
2024-02-13 | 22:30-02:00 | Home | Application | Ali Suhail | Complete Workout History Screen Implement Delete Functionality | Complete | Completed 80% of Workout History Screen Implemented Delete Functionality
2024-02-14 | 22:30-01:30 | Home | Application | Ali Suhail | Complete Workout History Screen Implement Update Functionality | Complete | Completed 80% of Workout History Screen Implemented Update Functionality
2024-02-20 | 11:30-03:00 | Home | Application | Ali Suhail | Complete Workout History Screen | Complete
2024-02-21 | 08:30-12:30 | Home | Application | Ali Suhail | Fix Github problem (Long Paths & Size Limiter) Start Exercise Log Screen Implement Delete Exercise Log Functionality | Complete | Fixed Github Problem Implemented Delete Exercise Log Functionality Completed 40% Exercise Log Screen
2024-02-22 | 22:00-01:30 | Home | Application | Ali Suhail | Complete Exercise Log Screen Implement Update Exercise Log Functionality | Complete | Implemented Exercise Log Screen Implemented Update Exercise Log Functionality
2024-02-23 | 13:30-14:10 | Online | Supervisor Meeting | Ali Suhail Eman Qaddoumi | Discuss Project Progress | Complete
2024-02-26 | 20:00-00:00 | Home | Application | Ali Suhail | Create Allocate Workout Screen Implement Delete Workout Functionality Implement Update Workout Functionality | Complete | Created Allocate Workout Screen Implemented Delete Workout Functionality Implemented Update Workout Functionality
2024-03-01 | 12:00-16:00 | Home | Application | Ali Suhail | Complete Allocate Workout Screen Implement Allocate Workout Functionality Implement Create Workout Functionality | Complete | Completed Allocate Workout Screen Completed 30% Allocate Workout Functionality Completed 5% Create Exercise Funtionality
2024-03-03 | 23:00-04:00 | Home | Application | Ali Suhail | Implement Create Workout Functionality Implement Create Exercise Functionality | Complete | Implemented Create Workout and Create Exercise Functionality
2024-03-05 | 22:00-02:40 | Home | Application | Ali Suhail | Implement Allocate Exercise Functionality Implement Update Exercise Functionality Implement Delete Exercise Functionality | Complete | Implemented Update and Delete Exercise Functionality Completed 50% Allocate Exercise Functionality
2024-03-08 | 17:00-20:30 | Home | Application | Ali Suhail | Implement Allocate Exercise Functionality Create Gym Finder Screen Create Allocate Exercise Log Screen | Complete | Implemented Allocate Exercise Functionality Created Gym Finder Screen Created Allocate Exercise Log Screen
2024-03-09 | 19:00-21:00 | Home | Application | Ali Suhail | Implement Allocate Exercise Log Screen Fix Bugs in Allocate Exercise Screen | Complete | Implemented Allocate Exercise Log Screen
2024-03-20 | 20:00-02:00 | Home | Application | Ali Suhail | Update Requirements Update Final Report | Complete
2024-03-21 | 20:00-12:30 | Home | Application | Ali Suhail | Update Usecase Diagrams Update Class Digrams | Complete
2024-03-22 | 20:00-12:30 | Home | Application | Ali Suhail | Update Usecase Descriptions Update Class Diagrams Write Requirement Section | Complete
2024-03-23 | 20:00-12:30 | Home | Application | Ali Suhail | Update Database Schema for LocalDB and CentralDB Write Methodology Section | Complete
2024-03-24 | 23:00-04:00 | Home | Application | Ali Suhail | Write Design Section | Complete
2024-03-25 | 20:00-03:30 | Home | Arduino Watch | Ali Suhail | Implement Date and Time Functionality Implement Blood Oxygen Functionality Implement Heart Rate Functionality | Complete | Implemented Blood Oxygen Functionality Implemented Heart Rate Functionality
2024-03-27 | 17:30-18:30 | Online | Supervisor Meeting | Ali Suhail Eman Qaddoumi | Discuss Draft Report | Complete | Move Table Heading to top. Add a Flowchart of the overall project. Include all table/diagram in the report. Add introduction/summary in each chapter.
2024-03-31 | 20:00-01:30 | Home | Report | Ali Suhail | Move Table Heading to top. Add a Flowchart of the overall project. Include all table/diagram in the report. Add introduction/summary in each chapter. | Complete
2024-04-01 | 20:00-01:30 | Home | Arduino Watch | Ali Suhail | Implement SD card data collection Report Evaluation | Complete | Completed Report Evaluation Partially Implemented SD card data logging
2024-04-03 | 21:00-01:00 | Home | Arduino Watch | Ali Suhail | Implement SD card data collection | Complete | Completed Implemented SD card data logging
2024-04-04 | 18:00-00:00 | Home | Arduino Watch | Ali Suhail | Start Work with Bluetooth Functionality | Complete
2024-04-05 | 19:30-23:00 | Home | Arduino Watch | Ali Suhail | Test Bluetooth LE Functionality | Complete
2024-04-06 | 19:30-23:00 | Home | Arduino Watch | Ali Suhail | Test Bluetooth LE Functionality | Complete
2024-04-09 | 20:00-03:00 | Home | Arduino Watch | Ali Suhail | Implement Bluetooth connection between Android and Arduino Watch | Complete
2024-04-10 | 21:00-06:15 | Home | Arduino Watch | Ali Suhail | Implement Bluetooth connection between Android and Arduino Watch | Complete
2024-04-11 |  | Home | Arduino Watch | Ali Suhail | Transfer data between Arduino Watch and Andriod phone | Complete